## User Stories
Project:	sharemycode.net			Description:
Document:	Product Backlog
Code:	DC02
Version:	0.1
Author:	Lachlan Archibald
Date Modified:	11/09/14

User Stories
ID	Theme	User group	I want to...	So that...	Sprint Assigned	Status (%)	Completed date	Related to Tasks	Priority	Story points	Comments
US01	Registration	User	Register for the sharemycode service	My account is created and I am able to login and use the sharemycode product	Sprint 1	100	09/09/14	DT07, DT08, DT11, DT12,DT24	1
US02	Authentication	User	Be able to login to the service and have my actions authenticated	I can perform tasks on the service relating to my user account.	Sprint 1	20		DT33, DT34, DT35, DT36	1
US03	Authentication	User	Be able to logout of the service	I can de-authenticate when I have finished performing my tasks, so that my account cannot be used without my knowledge.	Sprint 1	10		DT33, DT34, DT35, DT37	3
US04	Projects	User	Create a new project on the sharemycode service	I can upload project resources and manage the project details online	Sprint 1	50		DT09, DT13, DT14	1
US05	Projects	User	Upload project files	My project files can be attached to the project I have created, and are available to the service	Sprint 1	20		DT15, DT16, DT46	2
US06	Projects	User	Create project resources	I can create new files for my project	Sprint 1	60		DT18, DT17, DT47, DT48,DT49	2
US07	Projects	User	Convert project resources	My uploaded files are converted into resources and attached to my project.	Sprint 1	70		DT18, DT17, DT47, DT48,DT50	2
US08	Projects	User	List projects	I can view a list of projects	Sprint 1	70		DT42	3
US09	Projects	User	Fetch project	I can view project information and download the project to my client	Sprint 1	60		DT44	3
US10	Projects	User	Persist my project	My project information is not lost on the server	Sprint 1	100	25/08/14	DT23	1
US11	Projects	User	Delete my project	I can remove my project from the service when it is no longer needed.	Sprint 1	0		DT43	4
US12	Projects	User	List resources	I can view the list of resources relating to my project	Sprint 1	80		DT20	3
US13	Projects	User	Fetch resources	I can view or modify my project resources by downloading them to my client.	Sprint 1	80		DT21	2
US14	Projects	User	Delete resources	I can remove a resource from my project	Sprint 1	0		DT19	3
US15	Projects	User	Subscribe to resource updates	I can automatically receive updates to projects that I am subscribed to	Sprint 1	0		DT26, DT50	4
US16	Projects	User	Publish resource updates	When I modify resources in my client, I can publish the updates to my online project	Sprint 1	0		DT27, DT50	4
US17	Projects	User	Authorise other users to access and modify my project with a range of access levels	My project can be access and modified for support or collaboration purposes	Sprint 1	0		DT25, DT46	3
US18	Projects	User	Update the authorisation of other uses to access my project	I can change the level of access that a user has to my project	Sprint 1	0		DT28, DT46	3
US19	Projects	User	Remove authorisation of users to access my project.	I can remove authorised users that should no longer be allowed to view or modify my project	Sprint 1	0		DT29, DT46	3
US20	Projects	User	Fetch the access level of a user to my project	I can view the level of access that another user has for my project	Sprint 1	0		DT30	3
US21	Users	User	Update my user account details	Change my email address and password	Sprint 1	0		DT51, DT52	2
US22	Users	User	Find another user by username	Provide access to my projects	Sprint 1	60		DT53	2
US23	Users	User	Find another user by email	Provide access to my projects	Sprint 1	60		DT54	2
US24	Clients	User	Use the website client to access the service	I can access the service from the website	Sprint 3	10		DT32, DT39	4
US25	Clients	User	Use an IDE plugin to access the service	I can access the server from my favourite IDE	Sprint 3	0		DT38	4
US26	Clients	Developer	Have access to a sharemycode client library	I can write my own client applications to access the service	Sprint 2	10		DT31	2
US27	Synchronisation	User	Have my project resources synchronise in real time with my IDE	I and my peers can work on the same project together	Sprint 3	0		DT40, DT41, DT50, DT26, DT27	5
US28	Projects	User	Be able to generate code using a third party tooling service	I can easily add new functionality to my project.	Sprint 3	0		DT25	4

## Development Tasks
Development Tasks
ID	Theme	Name	Area	Description	Priority	Sprint Assigned	Status (%)	Completed date	Related to Tasks	Comments
DT01	Initialisation	Development Environment Setup	Entire Project			Sprint1	100
DT02	Initialisation	Create project in Eclipse	Entire Project			Sprint1	100
DT03	Initialisation	Add Maven Dependencies	Entire Project			Sprint1	100
DT04	Initialisation	Service REST Endpoint setup	Service			Sprint1	100
DT05	Initialisation	Entity Creation	Service			Sprint1	100
DT06	Testing	Basic HTML Frontend – Testing	Service			Sprint1	100
DT07	Registration	Registration REST Endpoint setup	Service			Sprint1	100
DT08	Users	Users REST Endpoint setup	Service			Sprint1	90
DT09	Projects	Projects REST Endpoint setup	Service			Sprint1	80
DT10	Projects	Resources REST Endpoint setup	Service			Sprint1	60
DT11	Registration	User Registration	Service			Sprint1	100
DT12	Registration	User Registration – UI	Webclient			Sprint1	100
DT13	Projects	Project Creation	Service			Sprint1	100
DT14	Projects	Project Creation – UI	Webclient			Sprint1	90
DT15	Projects	Project File uploads	Service			Sprint1	90
DT16	Projects	Project File uploads – UI	Webclient			Sprint1	90
DT17	Projects	Project File Extraction	Service			Sprint1	100
DT18	Projects	Project Resource Creation	Service			Sprint1	100
DT19	Projects	Delete resource	Service			Sprint1	0
DT20	Projects	List resources	Service			Sprint1	100
DT21	Projects	Fetch resource	Service			Sprint1	100
DT22	Database	Implement H2 In-Memory Database	Service			Sprint1	100
DT23	Database	Project Persistence	Service			Sprint1	100
DT24	Database	User Persistence	Service			Sprint1	100
DT25	Projects	Authorise Users to access project	Service			Sprint1	0
DT26	Projects	Resource update subscription	Service			Sprint1	0
DT27	Projects	Publish Resource Update	Service			Sprint1	0
DT28	Projects	Update Authorisation	Service			Sprint1	0
DT29	Projects	Remove Authorisation	Service			Sprint1	0
DT30	Projects	Fetch access level	Service			Sprint1	0
DT31	Client	Java Client Library Development	Client			Sprint2	40
DT32	Client	New Webclient for Testing – Javascript | AngularJS | Xwidgets	Client			Sprint2	50
DT33	Security	Security Integration	Service			Sprint2	50
DT34	Security	Authentication REST Endpoint setup	Service			Sprint2	50
DT35	Security	User Authentication	Service			Sprint2	50
DT36	Security	User Authentication/Login – Client	Client			Sprint2	50
DT37	Database	Implement MySQL database	Service			Sprint2	0
DT38	Client	IDE Plugin development	Client			Sprint3	0
DT39	Client	Website Development	Website			Sprint3	10
DT40	Synchronisation	Operational Transformation Integration	Service			Sprint3	0
DT41	Synchronisation	Operational Transformation Integration – Client	Client			Sprint3	0
DT42	Projects	List Projects	Service			Sprint1	100
DT43	Projects	Delete Projects	Service			Sprint1	0
DT44	Projects	Fetch Project	Service			Sprint1	100
DT45	Projects	Resource Persistence	Service			Sprint1	100
DT46	Projects	Project Access Persistence	Service			Sprint1	100
DT47	Projects	Project Resource Persistence	Service			Sprint1	100
DT48	Projects	Resource Content Persistence	Service	Persist resource contents when created		Sprint1	100
DT49	Projects	Resource Content Creation	Service	Resource Contents store the byte data of Project Resources		Sprint1	100
DT50	Projects	Implement WebSockets	Service			Sprint3	0
DT51	Users	Update user account details	Service			Sprint1	0
DT52	Users	Update user account details – UI	Webclient			Sprint2	0
DT53	Users	Lookup user by username	Service			Sprint1	100
DT54	Users	Lookup user by email	Service			Sprint1	100
DT55
DT56
DT57

## Project Management Tasks
Project Management Tasks
ID	Name	Description	Sprint	Status %	Completed
PT01	Requirements Elicitation	Determine the project requirements for the upcoming sprint	Sprint1	100	08/08/14
PT02	UML Use Cases	Define a visual description of how the project can be used by the end users	Sprint1	100	10/08/14
PT03	UML Sequences	Define the sequence in which tasks can be achieved in the project	Sprint1	100	10/08/14
PT04	SRS	A document describing the requirements of the project throughout the development.	Sprint1	70
PT05	SDD	A document describing the design of project artifacts and how they change throughout development	Sprint1	0
PT06	Project Planning Report	A report describing how the project will be completed, the outcomes, aims and end result as expected	Sprint1	100	28/08/14
PT07	Unit Testing	Test cases for individual pieces of the project.	Sprint1	30
PT08	Arquillian Testing	Test cases for EJB/CDI aspects of the project. Server side	Sprint1	0
PT09	Product Backlog	A document describing the tasks of sprint 1, and their completion	Sprint1	50
PT10	Sprint Backlog	A document describing the tasks of sprint 1, the effort required and how the effort was spent	Sprint1	0
PT11	Requirements Elicitation	Determine the project requirements for the upcoming sprint	Sprint2	0
PT12	SRS	A document describing the requirements of the project throughout the development.	Sprint2	0
PT13	SDD	A document describing the design of project artifacts and how they change throughout development	Sprint2	0
PT14	Unit Testing	Test cases for individual pieces of the project.	Sprint2	0
PT15	Arquillian Testing	Test cases for EJB/CDI aspects of the project. Server side	Sprint2	0
PT16	Product Backlog	A document describing the tasks of sprint 1, and their completion	Sprint2	0
PT17	Sprint Backlog	A document describing the tasks of sprint 1, the effort required and how the effort was spent	Sprint2	0
PT18	Requirements Elicitation	Determine the project requirements for the upcoming sprint	Sprint3	0
PT19	SRS	A document describing the requirements of the project throughout the development.	Sprint3	0
PT20	SDD	A document describing the design of project artifacts and how they change throughout development	Sprint3	0
PT21	Unit Testing	Test cases for individual pieces of the project.	Sprint3	0
PT22	Arquillian Testing	Test cases for EJB/CDI aspects of the project. Server side	Sprint3	0
PT23	Product Backlog	A document describing the tasks of sprint 1, and their completion	Sprint3	0
PT24	Sprint Backlog	A document describing the tasks of sprint 1, the effort required and how the effort was spent	Sprint3	0
PT25
PT26
PT27
PT28
PT29
PT30

## IAP Tasks
IAP Tasks
ID	Name	Description	Due Date	Status %	Completed
IAP01	Health and Safety Induction		01/08/14	100	31/07/14
IAP02	Graduation Notification Form		03/11/14	100	01/08/14
IAP03	NDA Red Hat		03/08/14	100	31/07/14
IAP04	NDA Griffith		10/08/14	100	07/08/14
IAP05	Workplace Orientation Form		10/08/14	100	07/08/14
IAP06	Risk Assessment		29/08/14	100	28/08/14
IAP07	Project Planning Report		29/08/14	100	28/08/14
IAP08	Expo Requirements Form		17/10/14	100	12/09/14
IAP09	Seminar Presentation		30/09/14	0
IAP10	Seminar Abstract		30/09/14	10
IAP11	Professional Practice Report		17/10/14	0
IAP12	Thesis Title Notification Form		27/10/14	0
IAP13	Final Project Report		03/11/14	0
IAP14	Project Poster		05/11/14	0
IAP15	Technical Defence		06/11/14	0

## Documents
Documents
ID	Name	Version	Description	Status %	Comments
DC01	Project Planning Report	1	Describes the initial plan of the project, how tasks will be attempted and the expected outcomes and aims of the project	100
DC02	Product Backlog	0.2	List of project tasks and deliverables and their status throughout the project	Sprint 1
DC03	Software Requirements Specification (SRS)	0.1	Defines the requirements of the project and other specifications. Updated throughout the project.	Sprint 1
DC04	Software Design Document (SDD)	0.1	Defines design of project artifacts, and how these change throughout the project	Sprint 1
DC05	User Manual		A manual to assist the client to install and use the software product.	0
DC06
DC07
DC08
DC09
DC10
DC11
DC12
DC13
DC14
DC15
DC16
DC17
DC18
DC19
DC20
DC21
DC22
DC23
DC24
DC25
DC26
DC27
DC28
DC29
DC30