## Sprint 1
Sprint Backlog
Sprint:	1		Document Version	0.4
Start Date:	07/08/14		Date Modified:	16/09/14
End Date:	06/09/14		Tasks Completed:	29
Length (days):	30		Number of tasks:	35
			Sprint Completion:	83%

Task ID	Theme	Title	Component	Status	Complete	Date	Description	Notes	Tested	Test Notes
DT01	Initialisation	Development Environment Setup	Preparation	100	Yes	07/08/14
DT02	Initialisation	Create project in Eclipse	Preparation	100	Yes	07/08/14
DT03	Initialisation	Add Maven Dependencies	Preparation	100	Yes	07/08/14
DT04	Initialisation	Service REST Endpoint setup	Service	100	Yes
DT05	Initialisation	Entity Creation	Service	100	Yes
DT06	Testing	Basic HTML Frontend – Testing	Service	100	Yes
DT07	Registration	Registration REST Endpoint setup	Service	100	Yes
DT08	Users	Users REST Endpoint setup	Service	100	Yes
DT09	Projects	Projects REST Endpoint setup	Service	100	Yes
DT10	Projects	Resources REST Endpoint setup	Service	100	Yes
DT11	Registration	User Registration	Service	100	Yes
DT12	Registration	User Registration – UI	Webclient	100	Yes
DT13	Projects	Project Creation	Service	100	Yes
DT14	Projects	Project Creation – UI	Webclient	90	No
DT15	Projects	Project File uploads	Service	90	No			Completed using multipart, but supervisor suggested we change to separate uploading of attachments
DT16	Projects	Project File uploads – UI	Webclient	90	No
DT17	Projects	Project File Extraction	Service	100	Yes
DT18	Projects	Project Resource Creation	Service	100	Yes
DT19	Projects	Delete resource	Service	50	No
DT20	Projects	List resources	Service	100	Yes
DT21	Projects	Fetch resource	Service	100	Yes
DT22	Database	Implement H2 In-Memory Database	Service	100	Yes
DT23	Database	Project Persistence	Service	100	Yes
DT24	Database	User Persistence	Service	100	Yes
DT42	Projects	List Projects	Service	100	Yes
DT43	Projects	Delete Project	Service	50	No
DT44	Projects	Fetch Project	Service	100	Yes
DT45	Projects	Project Resource Persistence	Service	100	Yes
DT46	Projects	Project Access Persistence	Service	100	Yes
DT47	Projects	Resource Content Persistence	Service	100	Yes
DT48	Projects	Resource Content Creation	Service	100	Yes
DT49	Users	Lookup user by username	Service	100	Yes
DT53	Users	Lookup user by email	Service	100	Yes
DT54	Testing	Setup Junit testing	Client	100	Yes
DT55	Testing	Setup Arquillian Testing	Service	0	No

## Sprint 2
Sprint Backlog
Sprint:	2		Document Version	0.5					Complete Tasks	55
Start Date:	07/09/14		Date Modified:	02/10/14					Incomplete Tasks	16
End Date:	06/10/14		Tasks Completed:	55
Length (days):	29		Number of tasks:	71
			Sprint Completion:	77%

Task ID	Theme	Title	Component	Status	Complete	Date	Description	Notes	Tested	Test Notes
DT14	Projects	Project Creation – UI	Webclient	100	Yes	14/09/14
DT15	Projects	Project File uploads	Service	100	Yes	17/09/14
DT16	Projects	Project File uploads – UI	Webclient	100	Yes	17/09/14
DT19	Projects	Delete Resource	Service	80	No	15/09/14		Problems with referential integrity
DT25	Projects	Authorise Users to access project	Service	100	Yes
DT26	Projects	Resource update subscription	Service	0	No
DT27	Projects	Publish Resource Update	Service	100	Yes	09/10/14			09/10/14
DT28	Projects	Update Authorisation – project	Service	100	Yes
DT29	Projects	Remove Authorisation - project	Service	100	Yes
DT30	Projects	Fetch access level – Current user, project	Service	100	Yes
DT31	Client	Java Client Library Development	Client	50	No
DT32	Client	New Webclient for Testing – Javascript | AngularJS | Xwidgets	Webclient	40	No
DT33	Security	Security Integration	Service	100	Yes	25/06/14
DT35	Security	User Authentication	Service	100	Yes
DT36	Security	User Authentication/Login – webclient	Webclient	100	Yes
DT43	Projects	Delete Project	Service	100	Yes	15/09/14		Problems with referential integrity
DT51	Users	Update user account details	Service	100	Yes	15/09/14
DT52	Users	Update user account details – UI	Webclient	90	No
DT55	Testing	Setup Arquillian Testing	Service	0	No
DT56	Projects	Delete Project Access	Service	50	No	15/09/14		Problems with referential integrity
DT57	Projects	Delete ResourceAccess	Service	50	No	15/09/14		Problems with referential integrity
DT58	Projects	Delete ResourceContent	Service	50	No	15/09/14		Problems with referential integrity
DT59	Users	Add UserProfile entity	Service	100	Yes	15/09/14
DT60	Users	UserProfile creation	Service	100	Yes	15/09/14
DT61	Users	Edit UserProfile – service	Service	100	Yes	16/09/14
DT62	Users	Edit UserProfile – webclient	Webclient	80	No
DT63	Projects	Add ProjectAttachment Entity	Service	100	Yes	16/09/14
DT64	Projects	Create Project Attachment – service	Service	100	Yes	16/09/14
DT65	Projects	Create ResourceAccess	Service	100	Yes	18/09/14
DT70	Client	Create User – Client Library	Client	100	Yes	18/09/14
DT71	Client	Create Project – Client Library	Client	100	Yes	18/09/14
DT72	Client	List Projects – Client Library	Client	100	Yes	18/09/14
DT73	Client	Fetch Project – Client Library	Client	100	Yes	18/09/14
DT74	Client	List Resources – Client Library	Client	100	Yes	18/09/14
DT75	Client	Create Attachment – Client Library	Client	20	No
DT76	Client	Create ProjectAttachment – webclient	Webclient	100	Yes	17/09/14
DT77	Projects	Get AccessLevel for Resource – Current user	Service	100	Yes	26/09/14
DT78	Projects	Get UserAuthorisation for Project	Service	100	Yes	26/09/14
DT79	Projects	Get UserAuthorisation for Resource	Service	100	Yes	26/09/14
DT80	Projects	Authorise user for resource	Service	100	Yes
DT81	Projects	Update authorisation for resource	Service	100	Yes
DT82	Projects	Remove authorisation for resource	Service	100	Yes
DT83	Security	Get Authentication status	Service	100	Yes	25/09/14
DT84	Security	Get Authentication status	Clilent	100	Yes	25/09/14
DT85	Projects	CreateProjectAuthorisation	Client	100	Yes	01/10/14			01/10/14
DT86	Projects	GetProjectAuthorisation	Client	100	Yes	01/10/14			01/10/14
DT87	Projects	UpdateProjectAuthorisation	Client	100	Yes	01/10/14			01/10/14
DT88	Projects	RemoveProject authorisation	Client	100	Yes	01/10/14			01/10/14
DT89	Projects	GetResourceAuthorisation	Client	100	Yes	01/10/14			01/10/14
DT90	Projects	CreateResourceAuthorisation	Client	100	Yes	01/10/14			01/10/14
DT91	Projects	UpdateResourceAuthorisation	Client	100	Yes	01/10/14			01/10/14
DT92	Projects	RemoveResourceAuthorisation	Client	100	Yes	01/10/14			01/10/14
DT93	Users	GetUserProfile – service	Service	100	Yes	02/10/14			02/10/14
DT94	Users	GetUserProfile – client library	Client	100	Yes	02/10/14			02/10/14
DT95	Users	Update UserProfile – service	Service	100	Yes	02/10/14			02/10/14
DT96	Users	Update userProfile – client library	Client	100	Yes	02/10/14			02/10/14
DT97	Users	Update user account – clientlibrary	Client	100	Yes	02/10/14			02/10/14
DT98	Projects	ListSharedProjects	Service	100	Yes	02/10/14			02/10/14
DT99	Projects	ListSharedProjects	ClientLIbrary	100	Yes	02/10/14			02/10/14
DT100	Projects	ListSharedProjects	Webclient	100	Yes	02/10/14		Doesn't look very pretty, need to update CSS	02/10/14
DT101	Projects	ListProjects – webclient	Webclient	100	Yes	01/10/14		Doesn't look very pretty, need to update CSS	01/10/14
DT102	Projects	Update Project – service	Service	100	Yes	09/10/14			09/10/14
DT103	Projects	Update project – client library	Client	100	Yes	09/10/14			09/10/14
DT104	Projects	Update project – webclient	Webclient		No
DT105	Projects	Update resource – client library	client	100	Yes	09/10/14			09/10/14
DT106	Projects	Update resource – webclient	webclient		No
DT107	Projects	CreateResource with data	Service	100	Yes	08/10/14			08/10/14
DT108	Projects	CreateResource – client library	Client	100	Yes	08/10/14			08/10/14
DT109	Projects	Create Resource – webclient	Webclient		No
DT110	Projects	Project detail view – webclient	Webclient	90	No			Doesn't look very pretty, need to update CSS
DT111	Projects	list Project resources (tree)	Webclient		No

## Sprint 3
Sprint Backlog
Sprint:	3		Document Version	0.6
Start Date:	07/10/14		Date Modified:	10/10/14
End Date:	31/10/14		Tasks Completed:	9
Length (days):	24		Number of tasks:	21
			Sprint Completion:	43%

Task ID	Theme	Title	Component	Status	Complete	Date	Description	Notes	Tested	Test Notes
DT37	Database	Implement MySQL database	Service	0	No
DT19	Projects	Delete Resource	Service	100	Yes	15/09/14
DT31	Client	Java Client Library Development	Client	50	No
DT32	Client	New Webclient for Testing – Javascript | AngularJS | Xwidgets	Webclient	40	No
DT52	Users	Update user account details – UI	Webclient	90	No
DT55	Testing	Setup Arquillian Testing	Service	0	No
DT56	Projects	Delete Project Access	Service	100	Yes	15/09/14
DT57	Projects	Delete ResourceAccess	Service	100	Yes	15/09/14
DT58	Projects	Delete ResourceContent	Service	100	Yes	15/09/14
DT62	Users	Edit UserProfile – webclient	Webclient	80	No
DT75	Client	Create Attachment – Client Library	Client	100	Yes
DT104	Projects	Update project – webclient	Webclient		No
DT106	Projects	Update resource – webclient	webclient		No
DT109	Projects	Create Resource – webclient	Webclient		No
DT110	Projects	Project detail view – webclient	Webclient	90	No			Doesn't look very pretty, need to update CSS
DT111	Projects	list Project resources (tree)	Webclient		No
DT112	Projects	Change Project Owner	Service	100	Yes	09/10/14			09/10/14
DT113	Projects	Change Project Owner	Client	100	Yes	09/10/14			09/10/14
DT114	Security	Logout user	Service	90	No			Waiting for PicketLink
DT115	Security	Logout user	Client	90	No			Waiting for PicketLink
DT73	Client	Fetch Project – Client Library	Client	100	Yes	10/10/14		Changed to download entire project files	10/10/14
DT116	Projects	Fetch Project – service	Service	100	Yes	10/10/14		Changed to download entire project files	10/10/14

DT26	Projects	Resource update subscription	Service	0	No			Removed from scope

## Summary
Sprint 1
Number of tasks	35
Complete Tasks	29
Incomplete Tasks	6
Percentage Complete	83%

Sprint 2
Number of tasks	71
Complete Tasks	55
Incomplete Tasks	16
Percentage Complete	77%

Sprint 3
Number of tasks	21
Complete Tasks	9
Incomplete Tasks	12
Percentage Complete	43%
Sprint 1 Completion
(06/09/2014)
Sprint 2 Completion
(29/09/2014)