## Sprint 1
Sprint Backlog
Sprint:	1		Document Version
Start Date:	07/08/14		Date Modified:	16/09/14
End Date:	06/09/14		Tasks Completed:	29
Length (days):	30		Number of tasks:	35
			Sprint Completion:	83%

Task ID	Theme	Title	Component	Status	Complete	Date	Description	Notes	Tested	Test Notes
DT01	Initialisation	Development Environment Setup	Preparation	100	Yes	07/08/14
DT02	Initialisation	Create project in Eclipse	Preparation	100	Yes	07/08/14
DT03	Initialisation	Add Maven Dependencies	Preparation	100	Yes	07/08/14
DT04	Initialisation	Service REST Endpoint setup	Service	100	Yes
DT05	Initialisation	Entity Creation	Service	100	Yes
DT06	Testing	Basic HTML Frontend – Testing	Service	100	Yes
DT07	Registration	Registration REST Endpoint setup	Service	100	Yes
DT08	Users	Users REST Endpoint setup	Service	100	Yes
DT09	Projects	Projects REST Endpoint setup	Service	100	Yes
DT10	Projects	Resources REST Endpoint setup	Service	100	Yes
DT11	Registration	User Registration	Service	100	Yes
DT12	Registration	User Registration – UI	Webclient	100	Yes
DT13	Projects	Project Creation	Service	100	Yes
DT14	Projects	Project Creation – UI	Webclient	90	No
DT15	Projects	Project File uploads	Service	90	No			Completed using multipart, but supervisor suggested we change to separate uploading of attachments
DT16	Projects	Project File uploads – UI	Webclient	90	No
DT17	Projects	Project File Extraction	Service	100	Yes
DT18	Projects	Project Resource Creation	Service	100	Yes
DT19	Projects	Delete resource	Service	50	No
DT20	Projects	List resources	Service	100	Yes
DT21	Projects	Fetch resource	Service	100	Yes
DT22	Database	Implement H2 In-Memory Database	Service	100	Yes
DT23	Database	Project Persistence	Service	100	Yes
DT24	Database	User Persistence	Service	100	Yes
DT42	Projects	List Projects	Service	100	Yes
DT43	Projects	Delete Project	Service	50	No
DT44	Projects	Fetch Project	Service	100	Yes
DT45	Projects	Project Resource Persistence	Service	100	Yes
DT46	Projects	Project Access Persistence	Service	100	Yes
DT47	Projects	Resource Content Persistence	Service	100	Yes
DT48	Projects	Resource Content Creation	Service	100	Yes
DT49	Users	Lookup user by username	Service	100	Yes
DT53	Users	Lookup user by email	Service	100	Yes
DT54	Testing	Setup Junit testing	Client	100	Yes
DT55	Testing	Setup Arquillian Testing	Service	0	No

## Sprint 2
Sprint Backlog
Sprint:	2		Document Version
Start Date:	07/09/14		Date Modified:	16/09/14
End Date:	06/10/14		Tasks Completed:	12
Length (days):	29		Number of tasks:	28
			Sprint Completion:	43%

Task ID	Theme	Title	Component	Status	Complete	Date	Description	Notes	Tested	Test Notes
DT14	Projects	Project Creation – UI	Webclient	100	Yes	14/09/14
DT15	Projects	Project File uploads	Service	90	No
DT43	Projects	Delete Project	Service	100	Yes	15/09/14
DT19	Projects	Delete Resource	Service	100	Yes	15/09/14
DT57	Projects	Delete Project Access	Service	100	Yes	15/09/14
DT58	Projects	Delete ResourceAccess	Service	100	Yes	15/09/14
DT59	Projects	Delete ResourceContent	Service	100	Yes	15/09/14
DT16	Projects	Project File uploads – UI	Webclient	90	No
DT25	Projects	Authorise Users to access project	Service	0	No
DT26	Projects	Resource update subscription	Service	0	No
DT27	Projects	Publish Resource Update	Service	0	No
DT28	Projects	Update Authorisation	Service	0	No
DT29	Projects	Remove Authorisation	Service	0	No
DT30	Projects	Fetch access level	Service	0	No
DT31	Client	Java Client Library Development	Client	40	No
DT32	Client	New Webclient for Testing – Javascript | AngularJS | Xwidgets	Client	40	No
DT33	Security	Security Integration	Service	70	No
DT35	Security	User Authentication	Service	50	No
DT36	Security	User Authentication/Login – Client	Client	50	No
DT51	Users	Update user account details	Service	100	Yes	15/09/14
DT52	Users	Update user account details – UI	Webclient	90	No
DT55	Testing	Setup Arquillian Testing	Service	0	No
DT60	Users	Add UserProfile entity	Service	100	Yes	15/09/14
DT61	Users	UserProfile creation	Service	100	Yes	15/09/14
DT62	Users	Edit UserProfile – service	Service	100	Yes	16/09/14
DT63	Users	Edit UserProfile – client	Webclient	80	No
DT64	Projects	Add ProjectAttachment Entity	Service	100	Yes	16/09/14
DT65	Projects	Create Project Attachment – service	Service	100	Yes	16/09/14

## Sprint 3
Sprint Backlog
Sprint:	2		Document Version
Start Date:	07/10/14		Date Modified:	16/09/14
End Date:	31/10/14		Tasks Completed:	0
Length (days):	24		Number of tasks:
			Sprint Completion:	#DIV/0!

Task ID	Theme	Title	Component	Status	Complete	Date	Description	Notes	Tested	Test Notes
DT37	Database	Implement MySQL database	Service